## Marketing Campaign Tracker
Marketing Campaign Tracker
COMPANY NAME
Event name: [Fourt Coffee Gala] | Time to event | Task duration | Due date | Complete | Partner | Owner
Planning
Call front desk attendant to reserve room at hotel. | 8 weeks | 30 minutes | 2004-03-20 | 2004-12-05 | Alpine Ski House | Tina O'Dell
E-mail promotional form to <contact name> | 6-7 weeks | 2 days |  |  | A. Datum Corp. | Kim Ralls
Send invitation in e-mail for review to local account manager. | 5–6 weeks | 6 days | _ | _ | Alpine Ski House
Account manager sends back invitation approval. | 5–6 weeks | 1 day | 2004-03-01 | _
Preparation
Send event slide set in e-mail to account manager for review. | 2–3 weeks |  |  |  | A. Datum Corporation
Deployment
Order catering through front desk attendant. | 1 week
Partner calls registered attendees to confirm. | 2 days
Follow-up
Follow up with attendees who did not show up for the event. | Day after