## Issue Management Log
ISSUE MANAGEMENT LOG
Project Name
# | Current Status | Priority | Detail Description of Issue | Who Should Resolve? | Expected Resolution Date | Escalation Required (Y/N)? | Impact of the Issue Summary | Action Steps to Resolve the Issue | Issue Type | Date Identified | Assoc ID | Entered By | Actual Resolution Date | Final Resolution & Rationale
| Closed | Low | EXAMPLE: Issues raised by board members about the financial viability of the project are preventing the project from moving forward as planned. |  |  | No | EXAMPLE: Potential project stoppage | EXAMPLE: Meet with board members to clarify the project finances | Informational | 2006-01-01 |  | John Doe |  | EXAMPLE: The project team met with board members to clarify the project finances, allowing the project to move forward as planned.
| Work In Progress | Low | EXAMPLE: The project is short on a specific skill set. |  |  | No | EXAMPLE: Possibility of project work not completed on time | EXAMPLE: Add staff to fill the skills gap. | Procedural | 2006-01-01 |  | Jane Doe |  | EXAMPLE: Staff was added to the project to fill the skills gap.
| Closed | Low | EXAMPLE: Negotiations with functional managers in an organization competing for scarce human resources are forecasted to delay project completion. |  |  | No | EXAMPLE: Possability of project work not completed on time | EXAMPLE: Additional negotiation | System | 2006-01-01 |  | Tom Doe |  | EXAMPLE: Negotiations ended satisfactorily before they caused project delays.
|  | Low | [6 empty] | Other