## WBS
Work Breakdown Structure Sheet
[Company Name] | [Insert Name]
Project Manager: | Miko Do
Project Structure -Breakdown
WBS Code | Task Name | Assigned To | Start Date | End Date/Completion Date | Duration (Days) | Progress (%) | Status | Estimated Cost ($) | Actual Cost ($) | Difference ($)
1 | Project Initiation | Miko Do | 2025-01-15 | 2025-01-20 | 1900-01-04 | 100% | Completed | 500 | 500 | 0
1.1 | Stakeholder Meetings | Irho Lue | 2025-01-15 | 2025-01-16 | 1899-12-31 | 100% | Completed | 100 | 100 | 0
1.2 | Requirement Gathering | Miko Do | 2025-01-17 | 2025-01-20 | 1900-01-02 | 100% | Completed | 100 | 100 | 0
2 | Planning | Mary Johnson | 2025-01-21 | 2025-01-30 | 1900-01-08 | 50% | In Progress | 0 | 0 | 0
2.1 | Create Project Plan | Jane Smith | 2025-01-21 | 2025-01-25 | 1900-01-03 | 100% | Completed | 200 | 250 | -50
2.2 | Risk Assessment | Mary Johnson | 2025-01-26 | 2025-01-30 | 1900-01-03 | 0% | Not Started
3 | Execution | Team Alpha | 2025-02-01 | 2025-02-15 | 1900-01-13 | 0% | Not Started
Formulas:
Duration (Days) = IF([Start Date]="","",[End Date/Completion Date]-[Start Date])