## Construction Cost Estimate
Home Construction Expense Sheet
Project Information:
Project Name: |  |  |  | Total Budget: | 40000
Homeowner’s Name: |  |  |  | Prepared By:
Construction Start Date: |  |  |  | Date Prepared: | 2024-10-12
Expected Completion Date:
Expense Categories
1. Labor Costs
Description | Contractor/Worker | Estimated Cost ($) | Actual Cost ($) | Payment Date | Notes
General Contractor | ABC Builders | 5000 | 5200 | 2024-01-15 | Increased due to overtime
Electrician | Electric Pros | 3000 | 3000 | 2024-02-01 | Paid in full
Plumber | WaterWorks Co. | 2500 | 2400 | 2024-02-10 | Discount applied
Carpenter | Custom Carpentry | 4500
Labor Subtotal |  | 15000 | 10600
2. Material Costs
Description | Supplier | Estimated Cost ($) | Actual Cost ($) | Delivery Date | Notes
Lumber & Wood | Timber Supplies | 8000 | 7500 | 2024-01-05 | Paid upfront
Concrete | BuildRight Concrete | 4000 | 4100 | 2024-01-10 | Additional required
Electrical Supplies | Power Supplies Inc. | 1500 | 1400 | 2024-01-25
Plumbing Materials | Plumbing Depot | 1200 | 1300 | 2024-02-05
Flooring | FloorMart | 3500
Materials Subtotal |  | 18200 | 14300
3. Permit & Fees
Permit/Inspection | Authority | Estimated Cost ($) | Actual Cost ($) | Payment Date | Notes
Building Permit | City Hall | 1200 | 1200 | 2023-12-20 | Approved
Electrical Permit | County Office | 500 | 500 | 2023-12-22
Plumbing Permit | City Hall | 400
Inspection Fees | State Inspectors | 600
Permits & Fees Subtotal |  | 2700 | 1700
4. Miscellaneous Expenses
Description | Vendor | Estimated Cost ($) | Actual Cost ($) | Payment Date | Notes
Portable Restroom | Onsite Solutions | 600 | 500 | 2024-01-01 | Monthly rental
Dumpster Rental | Waste Management | 700 | 650 | 2024-01-05 | 2-month rental
Insurance | Construction Insure | 800
Cleanup Services | Sparkle Clean | 300
Miscellaneous Subtotal |  | 2400 | 1150
Total Project Costs
Category | Estimated Total ($) | Actual Total ($) | Notes
Labor | 15000 | 10600
Materials | 18200 | 14300
Permits & Fees | 2700 | 1700
Miscellaneous | 2400 | 1150
Total Estimated Costs | 38300 | 27750
Remaining Budget | 12250
Signature & Approval:
Prepared By:
Approved By:
Date of Approval: