## Project Name
Renovation Project Spreadsheet
Project Name: |  |  | Project Location:
Start Date: |  |  |  | End Date: |  |  | Remarks:
Search by Task ID:
3 | <--- Select Task ID from Drop Down
Task Description: | Plumbing Replacement
Task Assigned to: | GHI Plumbing Services
Task Completion Status: | Not Started
Renovation Project Tracker
Task ID | Task Description | Assigned To | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Variance (USD) | Status | Notes
1 | Demolition | ABC Contractors | 2024-01-01 | 2024-01-05 | 5000 | 4800 | 200 | Completed | Completed on schedule
2 | Electrical Wiring Upgrade | DEF Electric Co. | 2024-01-06 | 2024-01-10 | 8000 | 8200 | -200 | In Progress | Minor delay due to material issue
3 | Plumbing Replacement | GHI Plumbing Services | 2024-01-11 | 2024-01-15 | 6500 | 7200 | -700 | Not Started | Scheduled to begin next week
4 | Flooring Installation | JKL Flooring Co. | 2024-01-16 | 2024-01-20 | 7000 | 7400 | -400 | Not Started | Materials ordered
5 | Painting and Finishing | XYZ Painting Services | 2024-01-21 | 2024-01-25 | 4000 | 3800 | 200 | Not Started | Pending completion of flooring
|  | Expense Summary >>> |  | Total= | 30500 | 31400 | -900
Milestone Progress Tracker
Milestone | Planned Completion | Actual Completion | Status | Responsible Party | Notes | Add note…
Demolition Completed | 2024-01-05 | 2024-01-05 | Completed | ABC Contractors | On schedule
Electrical Wiring Done | 2024-01-10 |  | In Progress | DEF Electric Co. | Minor material delay
Plumbing Replacement | 2024-01-15 |  | Not Started | GHI Plumbing Services | Scheduled to start soon
Flooring Installed | 2024-01-20 |  | Not Started | JKL Flooring Co. | Materials ordered
Final Painting | 2024-01-25 |  | Not Started | XYZ Painting Services | Pending flooring completion