## Bath Remodel Costs
Bathroom Remodel Costs Worksheet
NOTE: Difference columns in table will show if actual went over estimated amounts. Red numbers show went over (negative) and black shows under numbers (positive).
|  |  | Itemized Cost ($) |  |  | Total Cost ($)
Area | Items | Quantity | Estimated | Actual | Difference | Estimated | Actual | Difference
Bath/Shower | Tub, cast iron, 5', standard | 1 | 250 | 254 | -4 | 250 | 254 | -4
Bath/Shower | Shower doors, hinged, standard | 1 | 200 | 212 | -12 | 200 | 212 | -12
Bath/Shower | Showerhead, standard | 1 | 50 | 65 | -15 | 50 | 65 | -15
Bath/Shower | Tub wall surround, standard | 1 | 200 | 209 | -9 | 200 | 209 | -9
Cabinets | Medicine cabinet 24'', deluxe | 1 | 200 | 209 | -9 | 200 | 209 | -9
Cabinets | Modular vanity 30'', standard | 2 | 100 | 112 | -12 | 200 | 224 | -24
Countertops | Ceramic tile, deluxe (qty. in lin. ft.) | 5 | 22.5 | 36 | -13.5 | 112.5 | 180 | -67.5
Faucets | Faucet, bathtub, standard | 1 | 90 | 100 | -10 | 90 | 100 | -10
Faucets | Faucet, shower, single handle, standard | 1 | 115 | 126 | -11 | 115 | 126 | -11
Faucets | Sink faucet, standard | 1 | 95 | 108 | -13 | 95 | 108 | -13
Flooring | Ceramic tile, standard (qty. in sq. ft.) | 35 | 12 | 24 | -12 | 420 | 840 | -420
Hardware | Towel bar, standard | 2 | 15 | 22 | -7 | 30 | 44 | -14
Hardware | Toilet Paper holder | 1 | 10 | 21 | -11 | 10 | 21 | -11
Lighting | Recessed lights, standard | 4 | 25 | 43 | -18 | 100 | 172 | -72
Sinks | Lavatory, standard | 2 | 60 | 80 | -20 | 120 | 160 | -40
Other |  | 1 | 20 | 33 | -13 | 20 | 33 | -13
Subtotal |  |  | 1464.5 | 1654 | -189.5 | 2212.5 | 2957 | -744.5
Unexpected Costs (add 30% estimated) |  |  | 439.35 |  |  | 663.75
Total costs |  |  | 1464.5 |  |  | 2876.25